## day 1
S.No | Date | Task | Link to useful video | Link to useful material | Time Taken | Errors Encountered Y/N | If Yes, share the Error & Solution in error report
1 | 27th Feb, 2017 | Create GitHub Repository | https://www.youtube.com/watch?v=FOtx1lO9SS4 | NA | 10 minutes | N | NA
2 | 27th Feb, 2017 | Installing Eclipse Mars, Attaching Apache Tomcat 8, Configuring Maven 3 | NA | NA | 20 minutes | N | NA
3 | 27th Feb, 2017 | Project Plan Documentation | NA | NA | 60 minutes | N | NA
4 | 27th Feb, 2017 | Installing webapp and documenting steps | NA | NA | 45 minutes | N | NA
5 | 27th Feb, 2017 | Creating the landing page | NA | http://www.sportxs.com/ | 90 minutes | N | NA
6 | 27th Feb, 2017 | Video Learning for github | https://www.youtube.com/watch?v=FOtx1lO9SS4 | NA | 15 minutes | N | NA
7 | 27th Feb, 2017 | Downloading , installing and uploading through git | https://www.youtube.com/watch?v=FOtx1lO9SS4 | NA | 60 minutes | Y | Github_Upload_Error
8 | 28th Feb , 2017 | Quiz | NA | NA | 75 minutes | N | NA
9 | 28th Feb , 2017 | SCRUM | https://www.youtube.com/watch?v=wx1UU7hhvbA https://www.youtube.com/watch?v=5FvK6zHzA4c | NA | 15 minutes | N | NA
10 | 28th Feb , 2017 | Login Page creation | NA | NA | 30 minutes | N | NA
11 | 28th Feb , 2017 | Registration Page creation | NA | NA | 50 minutes | N | NA
12 | 28th Feb , 2017 | Products Page Creation | NA | http://bootsnipp.com/snippets/featured/bootstrap-snipp-for-datatable | 30 minutes | N | NA
13 | 28th Feb , 2017 | Product Detail Page | NA | https://www.w3schools.com/bootstrap/bootstrap_ref_comp_glyphs.asp https://www.decathlon.in/p/8301689_onmove-50-gps-watch.html#/3-254-_ | 15 minutes | N | NA
14 | 28th Feb , 2017 | Creating link between pages | NA | NA | 10 minutes | N | NA
15 | 28th Feb , 2017 | Add depenency in pom.xml | https://www.youtube.com/watch?v=pU-4NybcjnE&list=PLBgMUB7xGcO1YY1J9NoXssmaB0FjLSbQ5 | NA | 10 minutes | N | NA
16 | 28th Feb , 2017 | Creating Dispatcher Servlet | https://www.youtube.com/watch?v=pU-4NybcjnE&list=PLBgMUB7xGcO1YY1J9NoXssmaB0FjLSbQ5 | NA | 40 minutes | N | NA
17 | 28th Feb , 2017 | Navigation using Spring | https://www.youtube.com/watch?v=pU-4NybcjnE&list=PLBgMUB7xGcO1YY1J9NoXssmaB0FjLSbQ5 | NA | 20 minutes | N | NA
18 | 28th Feb , 2017 | Loading Static Resources | https://www.youtube.com/watch?v=OuSElmnstN8&index=6&list=PLAXbOMavY3k1VJGqqhfqAn0tUSC14Qsvq | http://crunchify.com/spring-mvc-4-2-2-best-way-to-integrate-js-and-css-file-in-jsp-file-using-mvcresources-mapping/ https://www.mkyong.com/spring-mvc/spring-mvc-how-to-include-js-or-css-files-in-a-jsp-page/ | 50 minutes | Y | Mapping_error
19 | 28th Feb , 2017 | Common directory creation | https://www.youtube.com/watch?v=OuSElmnstN8&index=6&list=PLAXbOMavY3k1VJGqqhfqAn0tUSC14Qsvq | NA | 10 minutes | N | NA
20 | 28th Feb , 2017 | Documentation | NA | NA | 90 minutes | N | NA
21 | 1st Mar,2017 | Self Study for DAO | https://www.youtube.com/watch?v=9fVQ_mvzV48 https://www.youtube.com/watch?v=H1mePFyqqiE | NA | 20 minutes | N | NA
22 | 1st Mar,2017 | Quiz | NA | NA | 40 minutes | N | NA
23 | 1st Mar,2017 | Mock | NA | NA | 20 minutes | N | NA
24 | 1st Mar,2017 | Understanding OOD | NA | https://www.codeproject.com/Articles/93369/How-I-explained-OOD-to-my-wife | 10 minutes | N | NA
25 | 1st Mar,2017 | Creating Model class for Product | NA | NA | 20 minutes | N | NA
26 | 1st Mar,2017 | Creating IProductDAO and ProductDAOImpl | NA | NA | 40 minutes | N | NA
27 | 1st Mar,2017 | Creating Model class for Category | NA | NA | 10 minutes | N | NA
28 | 1st Mar,2017 | Creating ICategoryDAO and CategoryDAOImpl | NA | NA | 20 minutes | N | NA
29 | 1st Mar,2017 | Linking DAO with controller | https://www.youtube.com/watch?v=STi8nP7yArs | NA | 30 minutes | N | NA
30 | 1st Mar,2017 | List as datasource for table in products.jsp | https://www.youtube.com/watch?v=STi8nP7yArs | NA | 60 minutes | Y | Core_Tag_Error,Image_Visibility_Error
31 | 1st Mar,2017 | Route to ProductDetails page from Products page | NA | NA | 30 minutes | N | NA
32 | 1st Mar,2017 | Session on bower,node,data table | NA | NA | 40 minutes | N | NA
33 | 2nd Mar,2017 | adding spring dependency for using hibernate with H2 | NA | https://mvnrepository.com/artifact/org.springframework/spring-orm/4.2.2.RELEASE https://commons.apache.org/proper/commons-dbcp/ https://mvnrepository.com/artifact/org.springframework/spring-orm/5.0.0.M5 | 240 minutes | N | NA
34 | 2nd Mar,2017 | adding applicationContext.xml and connect it using web.xml | NA | NA | 20 minutes | N | NA
35 | 2nd Mar,2017 | Create Beans for DataSource, SessionFactory, TransactionManager in applicationContext.xml file. | NA | NA | 30 minutes | N | NA
36 | 2nd Mar,2017 | Put some sample data in the table and it should be retrieved in the Products Page in the datatable | NA | NA | 10 minutes | N | NA
37 | 2nd Mar,2017 | Write the Junit test cases for checking the DAO classes |  |  | Pending
38 | 3rd Mar,2017 | Quiz | NA | NA | 60 minutes | N | NA
39 | 3rd Mar,2017 | Sample data in database populated | NA | NA | 10 minutes | N | NA
40 | 3rd Mar,2017 | Modal implementation | NA | NA | 120 minutes | N | NA
41 | 3rd Mar,2017 | Videos | from 12
42 | 3rd Mar,2017 | Github url and settings | https://www.youtube.com/watch?v=dz6hUBdJPKc | NA | 20 minutes | N | NA
43 | 3rd Mar,2017 | Front end/web app creation | https://www.youtube.com/watch?v=dz6hUBdJPKc | NA | 15 minutes | Y | HttpSevlet_Error
44 | 3rd Mar,2017 | Back end/Quick start creation | https://www.youtube.com/watch?v=dz6hUBdJPKc | NA | 15 minutes | Y | BuildPath_Error
45 | 3rd Mar,2017 | Uploading github project from eclipse | https://www.youtube.com/watch?v=dz6hUBdJPKc | NA | 40 minutes | N | NA
46 | 3rd Mar,2017 | Adding configuration properties to both the projects. | https://www.youtube.com/watch?v=oPE6UO9yoK4 | https://mvnrepository.com/artifact/javax/javaee-api/7.0 https://www.mkyong.com/web-development/the-web-xml-deployment-descriptor-examples/ | 90 minutes | Y | JSF_Error
47 | 3rd Mar,2017 | Configuring Front Controller | https://www.youtube.com/watch?v=W44gqyCs0U4 | https://www.tutorialspoint.com/spring/spring_bean_definition.htm | 60 minutes | N | NA
48 | 3rd Mar,2017 | Creation of Front Day | https://www.youtube.com/watch?v=W44gqyCs0U4 | NA | 30 minutes | N | NA
49 | 3rd Mar,2017 | Creating master page |  |  | Pending
50 | 3rd Mar,2017 | Java configuration for hibernate in backend |  |  | Pending
51 | 4th Mar,2017 | Quiz | NA | NA | 30 minutes | N | NA
52 | 4th Mar,2017 | Mock | NA | NA | 30 minutes | N | NA
53 | 4th Mar,2017 | MVC Concept | NA | NA | 15 minutes | N | NA
54 | 4th Mar,2017 | View for requestparam and pathvariable | https://www.youtube.com/watch?v=IXg52Lg58m4 | NA | 10 minutes | N | NA
55 | 4th Mar,2017 | Creation of landing page and loading static resources | https://www.youtube.com/watch?v=OuSElmnstN8 | NA | 45 minutes | N | NA
56 | 4th Mar,2017 | Creation of master page | https://www.youtube.com/watch?v=qACqz8bMqSM&t=1s | NA | 70 minutes | N | NA
57 | 4th Mar,2017 | Creation of active menu | https://www.youtube.com/watch?v=zjiFBiNxdMI | NA | 40 minutes | N | NA
58 | 4th Mar,2017 | Creating DTO and DAO classes fro Products | https://www.youtube.com/watch?v=F2L24Cy4zkQ | NA | 30 minutes | N | NA
59 | 4th Mar,2017 | Adding dependencies | NA | NA | 30 minutes | N | NA
60 | 4th Mar,2017 | Linking backend project with UI | https://www.youtube.com/watch?v=STi8nP7yArs&t=38s | NA | 30 minutes | N | NA
61 | 4th Mar,2017 | Adding dependency inject @Autowired | https://www.youtube.com/watch?v=STi8nP7yArs&t=38s | NA | 10 minutes | N | NA
62 | 4th Mar,2017 | Side bar creation | https://www.youtube.com/watch?v=STi8nP7yArs&t=38s | NA | 20 minutes | N | NA
63 | 4th Mar,2017 | Creating DTO and DAO classes fro Category | https://www.youtube.com/watch?v=STi8nP7yArs&t=38s | NA | 60 minutes | N | NA
64 | 4th Mar,2017 | Design Products.jsp | https://www.youtube.com/watch?v=t15lMwO7Q28 | NA | 20 minutes | N | NA
65 | 4th Mar,2017 | Adding dynamic url for products | https://www.youtube.com/watch?v=t15lMwO7Q28 | NA | 20 minutes | N | NA
66 | 4th Mar,2017 | Configuring hibernate to work with h2 | https://www.youtube.com/watch?v=CV0g70poh_g&t=253s | NA | 30 minutes | N | NA
67 | 4th Mar,2017 | Making project functional till view all products | https://www.youtube.com/watch?v=CuygFw_H9hk | NA | 20 minutes | Y | Images_Error
68 | 4th Mar,2017 | Write test cases to work with ProductDAO | https://www.youtube.com/watch?v=S9wKr2nuHHw&t=25s | NA | 60 minutes | N | NA
69 | 4th Mar,2017 | Documentation | NA | NA | 30 minutes | N | NA
70 | 5th Mar,2017 | Hibernate form validation session | NA | http://websystique.com/springmvc/spring-4-mvc-form-validation-with-hibernate-jsr-validator-resource-handling-using-annotations/ | 60 minutes | N | NA
71 | 5th Mar,2017 | CRUD using hibernate | https://www.youtube.com/watch?v=rdYQOqxq9F0 | NA | 30 minutes | N | NA
72 | 5th Mar,2017 | Spring Forms | NA | http://websystique.com/springmvc/spring-4-mvc-form-validation-with-hibernate-jsr-validator-resource-handling-using-annotations/ | 60 minutes | N | NA
73 | 5th Mar,2017 | CRUD with spring forms-add | NA | http://websystique.com/springmvc/spring-4-mvc-form-validation-with-hibernate-jsr-validator-resource-handling-using-annotations/ | 70 minutes | N | NA
74 | 5th Mar,2017 | CRUD with spring forms-view with datatable | NA | http://websystique.com/springmvc/spring-4-mvc-form-validation-with-hibernate-jsr-validator-resource-handling-using-annotations/ | 20 minutes | N | NA
75 | 5th Mar,2017 | Hibernate form validation-dependency setup | NA | http://websystique.com/springmvc/spring-4-mvc-form-validation-with-hibernate-jsr-validator-resource-handling-using-annotations/ | 45 minutes | N | NA
76 | 6th Mar,2017 | Quiz | NA | NA | 30 minutes | N | NA
77 | 6th Mar,2017 | Hibernate validator correction | NA | http://websystique.com/springmvc/spring-4-mvc-form-validation-with-hibernate-jsr-validator-resource-handling-using-annotations/ | 270 minutes | Y | UnsatisfiedDependencyException_Error,ValiModelAttribute_Error,Validator_Error
78 | 6th Mar,2017 | Multipart Image upload-Dependencies addition | NA | https://mvnrepository.com | 10 minutes | N | NA
79 | 6th Mar,2017 | Multipart Image upload | NA | http://javabeat.net/spring-multipart-file-upload/ http://websystique.com/springmvc/spring-mvc-4-file-upload-example-using-commons-fileupload/ | 120 minutes | Y | MultipartUpload_Error
80 | 6th Mar,2017 | Understanding webflow | NA | http://www.jcombat.com/spring/create-your-first-spring-web-flow-based-web-application http://www.springbyexample.org/examples/simple-spring-web-flow-webapp-http://www.springbyexample.org/examples/simple-spring-web-flow-webapp-spring-config.html spring-config.html | 10 minutes | N | NA
81 | 6th Mar,2017 | Creation of registration page | NA | NA | 30 minutes | N | NA
82 | 6th Mar,2017 | User model creation | NA | NA | 20 minutes | N | NA
83 | 6th Mar,2017 | User DAO creation | NA | NA | 15 minutes | N | NA
84 | 6th Mar,2017 | User DAOIMPL | NA | NA | 10 minutes | N | NA
85 | 6th Mar,2017 | Updation of navbar to add admin section | NA | NA | 5 minutes | N | NA
86 | 6th Mar,2017 | Documentation | NA | NA | 30 minutes | N | NA

## error report
Error ID | Full Error | Solution | Link
Github_Upload_Error | Permission Denied (publickey) | Has to copy the https url in place of the SSH one | https://gist.github.com/adamjohnson/5682757 https://confluence.atlassian.com/bbkb/permission-denied-publickey-302811860.html http://stackoverflow.com/questions/17383177/permission-denied-publickey-errors-on-windows-when-using-moovweb file:///C:/Program%20Files/Git/mingw64/share/doc/git-doc/git-remote.html
Mapping_error | Mapping not found for images,css or js i.e static resources | isELIgnored has to be set to false | NA
Core_Tag_Error | JSTL for core tags not found | add dependency in pom.xml : <dependency> <groupId>jstl</groupId> <artifactId>jstl</artifactId> <version>1.2</version> </dependency> | NA
Image_Visibility_Error | Image non visible in jsp | We only specified names of images in list,whicle fetching we used static resources references to access them ,eg: ${images}/${product.productImage} | NA
ContextComponentScan_Error | Multiple annotations found at this line: - schema_reference.4: Failed to read schema document 'http://www.springframework.org/schema/context/spring-context-3.0.xsd', because 1) could not find the document; 2) the document could not be read; 3) the root element of the document is not <xsd:schema>. - cvc-complex-type.2.4.c: The matching wildcard is strict, but no declaration can be found for element 'context:component-scan'. |  | http://stackoverflow.com/questions/28895990/schema-reference-failed-to-read-schema
HttpSevlet_Error | javax.servlet.http.HttpServlet was not found in build path | We have to include the Apache Tomcat Server to the project. | https://www.youtube.com/watch?v=oPE6UO9yoK4
BuildPath_Error | Warning for build path not able to find jre | Goto properties of the project , Java Build Path,double click JRE inside libraries , select alternative jre,then save | https://www.youtube.com/watch?v=oPE6UO9yoK4
JSF_Error | JavaServer Faces 2.2 requires Dynamic Web Module 2.5 or newer | In second document of 3rd march 2017 | https://www.youtube.com/watch?v=oPE6UO9yoK4
Images_Error | Images were not displayed after doing all the static resource loading | Ctrl+F5 in the browser , this clears the cache | NA
UnsatisfiedDependencyException_Error | UnsatisfiedDependencyException raised by code after adding validator | Code:<dependency> <groupId>org.jboss.logging</groupId> <artifactId>jboss-logging</artifactId> <version>3.3.0.Final</version> </dependency> | http://stackoverflow.com/questions/31547015/hibernate-5-java-lang-nosuchmethoderror-org-jboss-logging-logger-debugf
ValidModelAttribute_Error | valid and modelattribute were not working | @ModelAttribute("product") @Valid Product product | NA
Validator_Error | Validator was working but the errors were not displayed in the form | Add the following code inside the doAction() of ProductController class : if(result.hasErrors()) { ModelAndView model1 =new ModelAndView("page"); model1.addObject("title","Product Management"); model1.addObject("title","Product Management"); model1.addObject("userClickProductCRUD","true"); return model1;} | NA
MultipartUpload_Error | Image was not uploading | annotation from productImage has to be removed | NA